|  |
| --- |
| **Welcome, Inc.** **90 – Day Action Plan****October 1, 2021 – December 31, 2021****Goal 1 Lead Public Policy Agenda\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_** |
| **Objectives** | **Action Steps** | **Accountability** | **Timeline** | **Resources Needed** | **Success Metrics** |
| #1 Chair citywide effort to target one or two policy initiatives | * Reach out to key collaborators & partners
 | Board Public Policy Chair & board committee | 10/1/21 – 11/15/21 | Compile listCall/email | Committee formed with support from city leaders and key partners; Policy initiative identified |
| * Meet with mayor
 | Board ChairExecutive Director | By 11/15/21 | Not applicable |
| * Draft policy initiative
 | Board Public Policy Committee | By 12/31/21 | Point person to draft policy |
| #2 Engage board members in leading policy agenda |  |  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |
|  |  |  |  |